## Weekly Plan (From Week29)
Weekly Planning
Week 29/2026 | [7 empty] | REMARK
Production Area | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19
Line2 |  |  |  | Production with sticker biscoff 250g Froneri. |  |  |  | ProdX - Production downtime. 20JUL - Crumble 21JUL - Line 5 22JUL - n/a 23JUL - Line 2 24JUL - Spread
Line3 |  | No production * Buhler download program by Rienhard. * Domino Lane1&Lane6 (P'Wut) * 1P remove and modify plates and reinstall. | No production * 13:00-16:00 Test 1Px10 , 2 people (Team M) * Technical team to install air blow, guide and spacer. - Check with Pongthep
Line4 |  |  |  |  | PM - ProdX LAN connection
Line5
Crumble | F - No production |  |  | Test print date code on sticker 750g India Mat: Generic. + Crumble. Date code : India pattern ??? Operator: 10:00-12:00 (During Production team M)
Spread Filling
Week 30/2026
Production Area | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26
Line2 |  |  |  | ProdX with PM 8 hours ProdX 13:00-15:00 by Metler Toledo
Line3 |  |  | F - No production | F - No production
Line4
Line5 |  | Day Shift - PM - Moved. * ProdX by Metler Toledo/Banyat. * Lighting by Deline/Bank. * Change Gas flow meter by Deline/Bank. * Test Double stack MES by Tiew/Banyat. |  |  | * ProdX - Morning. * Test Double stack MES by Tiew/Banyat. - Morning.
Crumble |  | F - No production | [5 empty] | Can we do FA with new film , When film will be arriving ?
Spread Filling | F - No production ProdX 13:00-15:00 |  |  | ProdX 13:00-15:00 | ProdX 13:00-15:00 |  |  | 23-28 July no production ( Set new format for Prod-X ) Jar filling
Week 31/2026
Production Area | 2026-07-27 | 2026-07-28 (Holiday) | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
Line2 |  | Retail line production is running ???
Line3 | Cavanna Arrived * Setup Quality Induction * Setup Safety Induction * Work Permit & JSA |  |  | No production Day Shift 9:00-18:00 Cavanna - n/a CAMA - Modification of Machine Night Shift Production of 1Px50 | No production (Chang Over to 1Px10) Day Shift 9:00-18:00 Cavanna - n/a CAMA - Modification of Machine Night Shift Production of 1Px50 |  | ไฟดับกะเช้า | Cavanna and Cama arrived in Week31 to Week 32 Trapo , Jam sensor + lower minium speed. ONLINE Safety Training Change over to 1Px10 which date ??????
Line4
Line5 |  | Day Shift 8:00-18:00 hours * Cavanna - Punch List * Lighting by Deline/Bank. * Change Gas flow meter by Deline/Bank. * PM Activity Night shift * Continue PM. | Day Shift * Cavanna fix punchlist * 3:30 Test Run 2Px6 and Handover/Line clearance Night Shift * Production | 1:00 Provisional Acceptance Test CL2Px6 (4 hours) * Cavanna * Cama * Skilled - Capture OEE screen.
Crumble |  | F - No production | F - No production
Spread Filling
Week 32/2026
Production Area | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09
Line2 | Mulitpack 125x6x4 | Mulitpack 125x6x4 | Run 125g | To be confirmed by Cavanna 9:00-16:00 Change heater resister of flapfolder 4 hours. Can collect basic during this time Test 2 hours (need cookies send to packing + Upspeed for Animal feed)
Line3 | Cavanna 7:00 Start Changeover to 1Px10 by operator 9:00-12:00 Finetune without cookies 13:00-17:00 Run with Cookies Cama 9:00-15:00 Machine Modification. 15:00 Start Run 1Px10 (Commercial ) | Cavanna & Cama - 1 pallet 9:00-12:00 Fix issue before running 13:00-17:00 Run 1Px10 ( Commercial) | Run 1Px10 (4-6 hours) - 4 pallets Pre- Final Acceptance Test * Cavanna * Cama | Run 1Px10 - 5 pallets Final Acceptance Test | F - No production (PM) | F - No production (PM)
Line4
Line5
Crumble |  |  | F - No production | F - No production
Spread Filling
Week 33/2026 | [7 empty] | Receive Biscoff encraving for 1P Line ? To be confirmed
Production Area | 2026-08-10 | 2026-08-11 | 2026-08-12 - Holidays | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16
Line2 | [6 empty] | run
Line3 | [6 empty] | stop
Line4 |  |  |  |  | PM Plan |  | stop
Line5 | [6 empty] | stop
Crumble |  |  |  | F - No production | F - No production |  | run
Spread Filling | [6 empty] | stop
Week 34/2026
Production Area | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23
Line2
Line3
Line4
Line5 |  |  |  |  | Final Acceptance Test for SKILL - Capture OEE 2Px6 ???
Crumble | Provisional Acceptance Test (Production) - K. ประจวบ. | PM plan
Spread Filling
Week 35/2026
Production Area | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30
Line2 |  |  |  | PM - Planned
Line3 | F - No production
Line4
Line5 | 8:00-17:00 Change Over CL 2P Classic to EOY 2Px8 Cavanna Arrived * Setup Quality Induction * Setup Safety Induction | 8:00-11:00 Production EOY 3 pallets 3 hours. 11:00-16:00 Change Mold EOY to XL 11:00 Cavanna/Cama can start working , dry run. Cama Arrived PROD-X Setting | Commissioning XL XL 2px18x10 | Commissioning XL XL 2px18x10 | Commissioning XL XL 2px18x10 ( Metler Toledo product verification ) | C/O |  | Commissioning XL 2px10x8 XL 2Px18x10 CL 2P+2P ( requirement of packaging to Flure )
Crumble
Spread Filling
Week 36/2026
Production Area | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06
Line2
Line3
Line4
Line5 | Skilled Arrived Commissioning XL XL 2px10x8 | Commissioning XL C/O XL 2px10x8 ( Metler Toledo product verification ) Warehouse/Logistic Transport Test 2Px10x8 Transport Test 2Px18x10 | Commissioning XL XL 2px10x8 Successful Commissioning | C/O Line Release Transition to Production Commissioning XL XL 2px18x10 | Commissioning XL XL 2px18x10 Transition to Production |  |  | XL Commissioning
Crumble
Spread Filling
Week 37/2026
Production Area | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13
Line2
Line3
Line4
Line5 | Commercial Production XL 2px18x10 | Commercial Production XL 2px18x10 | Commercial Production XL 2px18x10
Crumble
Spread Filling
Week 38/2026
Production Area | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 39/2026
Production Area | Mon 21 Sep | Tue 22 Sep | Wed 23 Sep | Thu 24 Sep | Fri 25 Sep | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 40/2026
Production Area | Mon 28 Sep | Tue 29 Sep | Wed 30 Sep | Thu 1 Oct | Fri 2 Oct | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 41/2026
Production Area | Mon 5 Oct | Tue 6 Oct | Wed 7 Oct | Thu 8 Oct | Fri 9 Oct | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 42/2026
Production Area | Mon 12 Oct | Tue 13 Oct | Wed 14 Oct | Thu 15 Oct | Fri 16 Oct | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 43/2026
Production Area | Mon 19 Oct | Tue 20 Oct | Wed 21 Oct | Thu 22 Oct | Fri 23 Oct | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 44/2026
Production Area | Mon 26 Oct | Tue 27 Oct | Wed 28 Oct | Thu 29 Oct | Fri 30 Oct | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 45/2026
Production Area | Mon 2 Nov | Tue 3 Nov | Wed 4 Nov | Thu 5 Nov | Fri 6 Nov | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 46/2026
Production Area | Mon 9 Nov | Tue 10 Nov | Wed 11 Nov | Thu 12 Nov | Fri 13 Nov | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 47/2026
Production Area | Mon 16 Nov | Tue 17 Nov | Wed 18 Nov | Thu 19 Nov | Fri 20 Nov | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 48/2026
Production Area | Mon 23 Nov | Tue 24 Nov | Wed 25 Nov | Thu 26 Nov | Fri 27 Nov | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 49/2026
Production Area | Mon 30 Nov | Tue 1 Dec | Wed 2 Dec | Thu 3 Dec | Fri 4 Dec | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 50/2026
Production Area | Mon 7 Dec | Tue 8 Dec | Wed 9 Dec | Thu 10 Dec | Fri 11 Dec | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 51/2026
Production Area | Mon 14 Dec | Tue 15 Dec | Wed 16 Dec | Thu 17 Dec | Fri 18 Dec | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 52/2026
Production Area | Mon 21 Dec | Tue 22 Dec | Wed 23 Dec | Thu 24 Dec | Fri 25 Dec | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 1/2027
Production Area | Mon 4 Jan | Tue 5 Jan | Wed 6 Jan | Thu 7 Jan | Fri 8 Jan | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 2/2027
Production Area | Mon 11 Jan | Tue 12 Jan | Wed 13 Jan | Thu 14 Jan | Fri 15 Jan | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 3/2027
Production Area | Mon 18 Jan | Tue 19 Jan | Wed 20 Jan | Thu 21 Jan | Fri 22 Jan | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 4/2027
Production Area | Mon 25 Jan | Tue 26 Jan | Wed 27 Jan | Thu 28 Jan | Fri 29 Jan | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 5/2027
Production Area | Mon 1 Feb | Tue 2 Feb | Wed 3 Feb | Thu 4 Feb | Fri 5 Feb | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 6/2027
Production Area | Mon 8 Feb | Tue 9 Feb | Wed 10 Feb | Thu 11 Feb | Fri 12 Feb | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 7/2027
Production Area | Mon 15 Feb | Tue 16 Feb | Wed 17 Feb | Thu 18 Feb | Fri 19 Feb | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 8/2027
Production Area | Mon 22 Feb | Tue 23 Feb | Wed 24 Feb | Thu 25 Feb | Fri 26 Feb | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 9/2027
Production Area | Mon 1 Mar | Tue 2 Mar | Wed 3 Mar | Thu 4 Mar | Fri 5 Mar | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 10/2027
Production Area | Mon 8 Mar | Tue 9 Mar | Wed 10 Mar | Thu 11 Mar | Fri 12 Mar | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 11/2027
Production Area | Mon 15 Mar | Tue 16 Mar | Wed 17 Mar | Thu 18 Mar | Fri 19 Mar | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 12/2027
Production Area | Mon 22 Mar | Tue 23 Mar | Wed 24 Mar | Thu 25 Mar | Fri 26 Mar | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 13/2027
Production Area | Mon 29 Mar | Tue 30 Mar | Wed 31 Mar | Thu 1 Apr | Fri 2 Apr | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 14/2027
Production Area | Mon 5 Apr | Tue 6 Apr | Wed 7 Apr | Thu 8 Apr | Fri 9 Apr | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 15/2027
Production Area | Mon 12 Apr | Tue 13 Apr | Wed 14 Apr | Thu 15 Apr | Fri 16 Apr | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 16/2027
Production Area | Mon 19 Apr | Tue 20 Apr | Wed 21 Apr | Thu 22 Apr | Fri 23 Apr | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 17/2027
Production Area | Mon 26 Apr | Tue 27 Apr | Wed 28 Apr | Thu 29 Apr | Fri 30 Apr | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 18/2027
Production Area | Mon 3 May | Tue 4 May | Wed 5 May | Thu 6 May | Fri 7 May | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 19/2027
Production Area | Mon 10 May | Tue 11 May | Wed 12 May | Thu 13 May | Fri 14 May | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Week 20/2027
Production Area | Mon 17 May | Tue 18 May | Wed 19 May | Thu 20 May | Fri 21 May | Saturday | Sunday
Line2
Line3
Line4
Line5
Crumble
Spread Filling
Note on D26: Banyat Champachoke: Need Production Support
Note on H40: Banyat Champachoke: SAP down

## Week31&32
Week31
Wed 29 Jul
Line05 Pre-Provisional Acceptance Test CL2Px6 = 6 hours.
Cavanna: onsite is required.
Cama : onsite is not required but nice to have.
Skilled : onsite is not required.
Thu 30 Jul
Line05 Provisional Acceptance Test CL2Px6 = 6 hours.
Cavanna: onsite is required.
Cama : onsite is not required but nice to have.
Skilled : onsite is not required.
Line03
Day Shift - No production.
Cama - Machine modification for 1Px10 (if required)
Night Shift
Normal Production Run 1Px50
Fri 31 Jul
Line03
Day Shift - No production.
Cama - Machine modification for 1Px10 (if required)
Night Shift
Normal Production Run 1Px50
Week32
Mon 3 Aug
Line03
Morning: Fined tune the machine/ dry run by Cavanna and Cama.
Afternoon: Run production 1Px10
Tue 4 Aug
Line03
Morning: Fined tune machine / dry run by Cavanna and Cama.
Afternoon: Run production 1Px10.
Wed 5 Aug
Line03
Full day : Final Acceptance Test of 1Px10 by Cavanna and Cama.
Thu 6 Aug
Line03
Full day - Continue production run 1Px10

## Week35&36
[6 empty] | Line05 | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37
[6 empty] | Date | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | Remark
|  | System | Activity |  | Output | Status | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
L05 Fabrication |  |  | Number of Dough |  |  |  |  | 0 | 0
|  |  |  | Morning |  |  |  | C/O CL to EOY | Production EOY 2Px8 | Commissioning XL 2Px18 | Commissioning XL 2Px18 | Commissioning XL 2Px18 | C/O to XL 2Px10 | holidays | Commissioning XL 2Px10 | Commissioning XL 2Px10 (Transport Test) | Commissioning XL 2Px10 (Successful Commissioning) | C/O EOY to 2Px18 | Production XL 2Px18 |  |  | Production XL2Px18
|  |  |  | Afternoon |  |  |  |  | C/O to 2Px18 | [8 empty] | Production XL 2Px18
|  |  |  | Morning |  |  |  | Cavanna Arrived | [6 empty] | Skilled Arrived
|  |  |  | Afternoon |  |  |  |  | Cama arrived
Week 35 Plan
Mon 24 Aug - Change Over from 2P to EOY 2Px8
| 8:00-17:00 |  | Change over activity from Classic 2P to EOY 2Px8 | Operation |  |  |  | ■
Cama arrived for safety/quality induction
Cavanna arrived for safety/quaility induction
| Tue 25 Aug - Production Run EOY 2Px8 | [7 empty] | ■
| 8:00-12:00 | Production | Production Run EOY 2Px 8 = 3 pallets | Operation
| 13:00-16:00 | Oven | Change Mold from EOY to XL | Technical
| 13:00-17:00 | Flow Wrap | Cavanna Change Over from EOY to XL 2px10 and Dry run | Cavanna
| 13:00-17:00 | CAMA | Cama installation of new format part XL2Px10x8 | Cama
| Wed 26 Aug - Start WET commissioning of XL 2Px10 | [8 empty] | ■
| 8:00 - 16:00 | Oven | Oven Start - Tipping 4 Dough Bin | Operation
| 9:00 - 17:00 | Flow Wrap | Cavanna run WET commissioning of XL 2px10 | Cavanna
| 8:00 - 17:00 | Case Packer | Cama installation of new format part XL2Px10x8 (Continue) and Dry run | Cama
| 9:00 - 17:00 | Transport | Technical Team commissioning of Transport System XL 2px10 | Techical
| 9:00 - 17:00 | Palletizer | - | Operation
| Thu 27 Aug - WET Commissioning of XL 2px10x8 | [9 empty] | ■ |  |  |  | ■ |  | ■
| 8:00 - 16:00 | Oven | Oven Start - Tipping 6 Dough Bin | Operation | 3 Pallets of XL 2Px10
| 9:00 - 17:00 | Flow Wrap | Cavanna run WET commissioning of XL 2px10 | Cavanna
| 9:00 - 17:00 | Case Packer | Cama run WET commissioning of XL 2px10x8 | Cama
| 9:00 - 17:00 | Transport | Technical Team commissioning of Transport System XL 2px10x8 | Techical
| 9:00 - 17:00 | Palletizer | Operation manual palletizing | Operation
| 9:00 - 17:00 | Metler Toledo | Setup & Commissioning Checkweigher and X-Ray incl. Prod-X | Metler Toledo
| Fri 28 Aug - Change Over to XL2Px18x10 & Start WET Commissioning of XL 2Px18x10 | [10 empty] | ■ |  |  |  | ■ |  | ■ | ■
| 12:00 - 16:00 | Oven | Oven Start - Tipping 4 Dough Bin | Operation
| 8:00 - 12:00 | Flow Wrap | Cavanna Change Over from XL2Px10 to XL2Px18 - Including Training | Cavanna
| 13:00-17:00 | Flow Wrap | Cavanna Start WET commissioning for XL2Px18 | Cavanna
| 8:00 - 17:00 | Case Packer | Cama installation of new format part XL2Px18x10 | Cama
| 9:00 - 17:00 | Transport | Technical Team commissioning of Transport System XL 2px18 | Techical
| 9:00 - 17:00 | Palletizer | Operation manual palletizing | Operation
Sat 29 Aug - Fixing PunchList
| 8:00 - 16:00 | Oven | No Production | Operation
| 8:00 - 17:00 | Flow Wrap | Cavanna can work on fixing punchlist | Cavanna
| 8:00 - 17:00 | Case Packer | Cama can work on fixing punchlist | Cama
Week 36 Plan | Week 36 - Date/Time
Mon 31 Aug - WET Commissioning of XL 2px18x10.
| 8:00 - 16:00 | Oven | Oven Start - Tipping 8 Dough Bin | Operation | 4 Pallets XL2Px18
| 9:00 - 17:00 | Flow Wrap | Cavanna run WET commissioning of XL 2px18 | Cavanna
| 9:00 - 17:00 | Case Packer | Cama run WET commissioning of XL 2px18x10 | Cama
| 9:00 - 17:00 | Transport | Technical Team commissioning of Transport System XL 2px18x10 | Techical
| 9:00 - 17:00 | Palletizer | Skilled run WET commissioning of XL 2Px18x10 - Make atleast 4-5 pallets | Skilled
| 9:00 - 17:00 | Metler Toledo | Setup & Commissioning Checkweigher and X-Ray incl. Prod-X | Metler Toledo
Tue 01 Sept - Change Over to XL 2px10x8 and WET Commissioning XL2Px10x8
| 12:00 - 16:00 | Oven | Oven Start - Tipping 5 Dough Bin | Operation | 2 Pallets XL2Px10
| 8:00 - 12:00 | Flow Wrap | Cavanna Change Over from XL2Px18 to XL2Px10 - Include Training | Cavanna
| 13:00-17:00 | Flow Wrap | Cavanna run Wet Commissioning XL2Px10 | Cavanna
| 8:00 - 17:00 | Case Packer | Cama Change Over from XL2Px18x10 to XL2Px10x8 - Include Training. | Cama
| 9:00 - 17:00 | Transport | Operation runTrapo system | Operation
| 9:00 - 17:00 | Palletizer | Skilled run WET commissioning of XL 2Px10x8 - Make atleast 2-3 pallets | Skilled
| 17:00-19:00 | Warehouse | Truck Transport Test of Pallet XL2Px18x10 and XL2Px8x10 | Operation
Wed 02 Sept - Successful Commissioning of XL 2Px10x8
| 8:00 - 16:00 | Oven | Oven Start - Tipping 10 Dough Bin | Operation | 5 Pallets XL2Px10
| 9:00 - 17:00 | Flow Wrap | Cavanna run Successful Commissioning XL2Px10 | Cavanna
| 9:00 - 17:00 | Case Packer | Cama run Successful Commissioning XL2Px10x8 | Cama
| 9:00 - 17:00 | Transport | Operation run Trapo system | Operation
| 9:00 - 17:00 | Palletizer | Skilled run Successful Commissioning XL 2Px10x8 | Skilled
Thursday 03 Sept - Change Over to XL2Px18x10 and Transition to Production
| 8:00-11:00 | ALL | Change Over to XL2Px18x10 | Quality Team
| 11:00-12:00 | Quality | Line Released by Quality Team
| 12:00-17:00 | Oven | Oven Start - Tipping 4 Dough Bin | Operation
| 13:00-17:00 | ALL | Run Production XL2Px18x10 (Saleable Product) | Production
| 8:00-17:00 | ALL | Support Production by Cavanna, Cama, Skilled. | ALL
Friday 04 Sept - Transition to Production to run XL2Px18x10
| 8:00-17:00 | ALL | Run Production XL2Px18x10 (Saleable Product) | Operation
| 8:00-17:00 | ALL | Support Production by Cavanna, Cama, Skilled. | ALL
CVS
|  |  | X-Ray Validation by Metler | CVS
|  |  | Checkweight Validation Metler | CVS
|  |  | X-Ray Validation by Quality/Operation team | CVS
|  |  | Transition Week | CVS
|  |  | Transportation Test | CVS
|  |  | BBD MES | CVS
|  |  | ProdX verification | CVS
Training
Change over to XL Multipack by Cavanna
Cama change over training
Skilled change over training
Transition Week
Take sample for Quality 7 DU ( send to Lembeke 3 DU )
Cockpit readiness
The product we run is Operation mode, Run& hold as the FP
Q-Score
|  |  | Pest Control/Fumigation/Sanitization/Swap ? |  |  | n/a
Line Cleaning and Line Release
CHO Production
Commercial Production

## Readiness Check
Material
XL2Px10
| Single pack | metalized | on track
| Multi pack flim | transparent | on track
XL2Px18
| Single pack | transparent | monitoring
| Multi pack flim | transparent | monitoring
Machine
| Line5 for 28-7 punchlist | Cavanna send 1 shipment for punch list | Received | Tech
| Line3 for 1Px10 | CAMA | Monitoring
| Line 5 for XL | Cavanna send 1 shipment | Received | Tech